## Plan
[6 empty] | Month | October | [14 empty] | November | [29 empty] | December
|  | PLAN |  | ACTUAL |  | Date | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Activity | Person | START | DURATION | START | DURATION | Day | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F
Text Pre-Processing | Anthony | 2016-10-24 | 14
LCS - Classic Forwards | Joe | 2016-10-18 | 6 | 2016-10-18 | 3
LCS - Classic Backwards | Jeremy | 2016-10-24 | 7
LCS - Recursive space efficient | Joe | 2016-10-31 | 14 | 2016-11-15 | 4
LCS - B & B | Jeremy | 2016-11-07 | 14 | [38 empty] | Milestone: All LCS Algo. complete
Printing neatly | Ed | 2016-10-19 | 7 | 2016-10-19
Time and space complexity tests | Ed | 2016-11-14 | 14
| Joe | 2016-11-14 |  | 2016-11-25
Comparisons on corpus | Josselin | 2016-10-24 | 14
| Joe | 2016-10-24 |  | 2016-11-05 | 4
Technique for plagarism score | Jeremy | 2016-10-31 | 14 | [31 empty] | Milestone : Technique for plagarism score
| Ed | 2016-10-31
User interface :- Planning | Ed | 2016-10-24 | 14
| Anthony | 2016-10-24
User interface :- Development | Anthony | 2016-11-07 | 14 | [38 empty] | Milestone : UI complete
| Josselin | 2016-11-07
Optional: Advanced Pre-Processing | Anthony | 2016-11-21 | 7
Optional: Advanced Post-Processing | Josselin | 2016-11-21 | 7
Report | Joe | 2016-11-28 | 14 | 2016-11-28
| Jeremy | 2016-11-28 | 14
| Anthony | 2016-11-28 | 14
Presentation for defence | Ed | 2016-11-28 | 14
| Josselin | 2016-11-28 | 14
Colours | Anthony
Joe
Jeremy
Josselin
Ed